LED SCADA Platform Development Plan (SDP-001)

Version: 0.1
Status: In Progress
Purpose: Living engineering development and project tracking document for the LED SCADA platform.

## Project Objectives

Develop a scalable SCADA platform for LED display systems.

Implement remote monitoring and control using MQTT.

Build a secure web dashboard and backend.

Document, verify and test each development milestone.

## Project Workflow

| ☐ | Task ID | Phase | Task | Planned Date | Target Date | Actual Date | Status | Verification | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ☐ | P1-001 | Planning | Create Git repository |  |  |  | Not Started |  |  |
| ☐ | P1-002 | Environment | Install Python, Docker, VS Code |  |  |  | Not Started |  |  |
| ☐ | P1-003 | Environment | Verify development environment |  |  |  | Not Started |  |  |
| ☐ | P2-001 | Gateway | Create fake telemetry generator |  |  |  | Not Started |  |  |
| ☐ | P3-001 | MQTT | Install Mosquitto and test publish/subscribe |  |  |  | Not Started |  |  |
| ☐ | P4-001 | Backend | Create FastAPI backend |  |  |  | Not Started |  |  |
| ☐ | P5-001 | Dashboard | Develop live dashboard |  |  |  | Not Started |  |  |

## Weekly Development Cycle

☐ Research & Planning

☐ Implementation

☐ Verification & Testing

☐ Documentation Update

☐ Review & Next Steps

## Engineering Log

| Date | Objective | Work Completed | Issues / Risks | Next Action |
| --- | --- | --- | --- | --- |

## Progress Summary

Overall Progress: 0%
Current Phase: Planning
Current Milestone: Development Environment
Last Updated: July 12, 2026

Local gateway:

- Python service

- Controller protocol drivers

- MQTT client

- Local buffer/database

- Remote server:

- Mosquitto MQTT

- FastAPI backend

- PostgreSQL or TimescaleDB

- HTML/JavaScript dashboard

- Nginx reverse proxy

Handling internet interruptions

- keep the last brightness setting

- store telemetry locally

- retry the server connection

- upload missing historical data when reconnected

- raise an offline alarm after a defined timeout

- prevent repeated or duplicate commands

- 0–30 seconds without data: normal delay

- 30–120 seconds: warning

- more than 120 seconds: site offline

First Development stage:

Build a small proof of concept:

Display controller

↓

Python gateway

↓ MQTT

Remote Docker server

↓

Browser dashboard

Start with only:

- controller online/offline

- brightness readback

- brightness control

- temperature

- voltage

- alarm status

- historical graph

Once stable, add:

- cabinet/module-level status

- flashing alarms

- test patterns

- scheduled brightness

- user accounts

- multiple customer sites

- email or mobile notifications

MQTT is ideal for a SCADA system because it works like a postal service.

- The remote server is the post office (MQTT broker).

- The local gateway at the display site is a mail carrier that publishes telemetry and receives commands.

- The dashboard subscribes to updates and sends control commands.

## Example architecture

Internet

│

│

┌────────────────────┐

│ MQTT Broker        		│

│ scada.company.com  		│

│ Port 8883 (TLS)    		│

└─────────┬──────────┘

│

┌─────────┴──────────────┐

│                         			│

▼                         			▼

Browser Dashboard         		Site Gateway

(iPad/PC)                 		(Python)

│

Local LAN

│

┌───────────────────────┐

│ Colorlight / Mooncell    			│

│ Novastar / Sensors       			│

└───────────────────────┘

Telemetry

sites/Middle East/AVR/display01/telemetry

{

"time":"2026-07-10T16:00:01",

"brightness":65,

"temperature":43.8,

"voltage":4.82,

"current":31.5,

"status":"Healthy"

}

Alarm

sites/Middle East/AVR/display01/alarm

{

"alarm":"High Temperature",

"module":"D125",

"temperature":71.2,

"level":"Critical"

}

The dashboard can immediately:

- flash the module red

- play a sound

- send an email or push notification

Command

{

"command":"brightness",

"result":"OK",

"actual":70

}

payload Json

{

"command":"brightness",

"value":70

}

Gateway receives:

Brightness = 70%

Confirm Status

sites/Middle East/AVR/display01/status

{

"command":"brightness",

"result":"OK",

"actual":70

}

Heart Beat

sites/Middle East/AVR/display01/heartbeat

{

"online":true,

"version":"1.4.2",

"uptime":72653

}

Display Maps

sites

├── Toronto

│      ├── EQBank

│      │      ├── Display01

│      │      └── Display02

│      │

│      └── RogersCentre

│             ├── Ribbon01

│             └── Ribbon02

│

├── LasVegas

│      └── HardRock

│              ├── GuitarNorth

│              ├── GuitarSouth

│              └── GuitarRoof

├── Middle East

│      └── Pineapple

│              ├── Media Tower

│              ├── Fountain

│              └── Skydisplay

│

└── Vancouver

└── Oakridge Mall

Plan :

- Week 1: Development environment

- Week 2: MQTT and communication

- Week 3: Database and FastAPI backend

- Week 4: Dashboard, alarms, historical trends, deployment, and security

Project Folder :

LED-SCADA/

backend/

dashboard/

mqtt/

database/

docs/

## SCADA Learning Plan (Version 1)

### Day 1 – MQTT Fundamentals

- What is SCADA?

- Why MQTT is used

- Publish / Subscribe concept

- Broker, Topic, Client

- Install MQTT Explorer

- Connect to a public broker

Goal: Understand how industrial devices communicate.

### Day 2 – Mosquitto & JSON

- Install Mosquitto

- Publish messages

- Subscribe to messages

- JSON format

- Design telemetry packets

Example :

{

"Display":"EQ Bank",

"Voltage":4.82,

"Temp":43,

"Brightness":65,

"Status":"Healthy"

}

### Day 3 – Python + MQTT

- Install Paho MQTT

- Python Publisher

- Python Subscriber

- Simulate LED controllers

- Send brightness commands

Goal: Build your first software “controller.”

### Day 4 – Docker

- Install Docker

- Run MQTT Broker inside Docker

- Remote VPS

- User Authentication

- TLS Encryption

Goal: Create a production-ready MQTT server.

### Day 5 – LED Controller Integration

- Colorlight

- Mooncell

- NovaStar

- Read brightness

- Read temperature

- Read voltage

- Parse protocols

Goal: Connect to real hardware.

### Day 6 – Dashboard

- HTML

- JavaScript

- Live Dashboard

- Alarm indication

- Historical graphs

- Device status

Goal: See live data on the screen.